## Sheet1
Project imtegration management
1. Project charter
Inputs | Tools and techniques | Output
Business documents- Business case Benefits management plan | Expert judgement | Project charter
Agreements | Data gathering- Focus groups Brainstorming Interviews | Assumption log
EEF (Enterprise environmental factors) | Interpersonal and Team skills- Conflict management Facilitation Meetings management
OPA (Organisational process assets) | Meetings
2. Develop project management plan
Inputs | Tools and techniques | Output
Project charter | Expert Judgement | Project management plan
Output from other processes | Data gathering:- Brainstorming Checklist Focus groups Interviews
EEF (Enterprise environmental factors) | Team and interpersonal skills:- Conflict management Facilitation Meeting management
OPA (Organisational process assets) | Meetings
3. Direct and manage project work
Inputs | Tools and techniques | Output
Project management plan | Expert Judgement | Deliverables
Project documents:- Change logs Lessons learned register Milestone list Project schedule Project communications Risk report Risk register RTM | PMIS (project management information system) | WPD (work performance data)
Approved Change request | Meetings | Issue logs
EEF (Enterprise environmental factors) |  | Change requests
OPA (Organisational process assets) |  | Project management plan updates
Project document updates:- Lessons learned register Stakeholder register Risk register Activity List Assumption log Requirements documentation
OPA (Organisational process assets) updates
4. Manage project knowledge
Inputs | Tools and techniques | Output
Project management plan: All components | Expert Judgement | Lessons Learned register
Project documents: Lesson learned register Project team assignments Resource breakdown structure Stakeholder register Source selection criteria | Knowledge management | Project management plan updates: Any component
Deliverables | Information management | OPA updates
EEF (Enterprise environmental factors) | Team and interpersonal skills: Active Listening Facilitation Leadership Networking Political awareness
OPA (Organisational process assets)
5. Monitor and Control project work
Inputs | Tools and techniques | Output
Project management plan: Any component | Expert Judgement | Change requests
Project documents: Issue log Cost Schedule Risk Project activities | Data analysis: Trend analysis Variance analysis Root cause analysis | Work performance reports
Work performance information | Decision making: Voting | Project management plan updates
Agreements | Meetings | Project document updates
EEF (Enterprise environmental factors)
OPA (Organisational process assets)